## Sheet1
Module | Item | Level | Type | Status | Issue Date | Reselution date | Closure date
Create Lost | The data type of lostentry must be changeto string | critical | bug | fixed | 2014-02-26 | 2014-03-04 | 2014-03-04
Manage Admins | New method needed | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
Manage Losts | New method needed | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
Create FoundEntry | Load page with entries of both Found and NotFound status | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
UpdateAdmin | If the user clicked save button moe than once will update again even if no change | high | bug | fixed | 2014-03-05 | 2014-03-05 | 2014-03-05
Create Lost | Need to prevent user click save more than once for same lost | high | bug | fixed | 2014-03-05 | 2014-03-05 | 2014-03-05
Search Losts | If there is no results for the typed search values | high | bug | Notfixed | 2014-03-05