## Sheet1
Module | Item | Level | Type | Status | Issue Date | Reselution date | Closure date
Create Lost | The data type of lostentry must be changeto string | critical | bug | open | 2014-02-26
Manage Admins | New method needed | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
Manage Losts | New method needed | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
Search Losts | Not completed | high | bug | Notfixed | 2014-02-25
Create FoundEntry | Load page with entries of both Found and NotFound status | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25