## Sheet1
Module | Item | Level | Type | Status | Issue Date | Reselution date | Closure date
CreateLost | desription may be long,so we need TextArea rather than TextBox | minor | modification | fixed | 2014-02-24 | 2014-02-24 | 2014-02-24
SearchLosts | Design not compatible with mobile | high | bug | Notfixed | 2014-02-25
Create FoundEntry | The TextArea validation not set | high | bug | fixed | 2014-02-25 | 2014-02-25 | 2014-02-25
SearchLosts | Design not compatible with mobile | high | bug | Notfixed | 2014-02-25
Create New Lost | Error messages not compatible with it's fields | high | bug | fixed | 2014-02-24 | 2014-02-24 | 2014-02-24
SearchLost | Design not compatible with mobile | high | bug | Notfixed | 2014-02-25
Update Admin | Textboxnedeedfor Status |  |  | Notfixed | 2014-02-26
Manage Losts | Design not compatible with mobile | high | bug | Notfixed | 2014-02-26