## Sheet1
Module | Item | Level | Type | Status | Issue Date | Reselution date | Closure date
Login |  |  |  | closed
Create Admin |  |  |  | closed
CreateLost | desription may be long,so we need TextArea rather than TextBox | minor | modification | closed | 2014-02-24 | 2014-02-24 | 2014-02-24
Manage Admins |  |  |  | closed
Manage Losts |  |  |  | closed
SearchLosts | Design not compatible with mobile | high | bug | open | 2014-02-25
Create FoundEntry | The TextArea validation not set | high | bug | closed | 2014-02-25 | 2014-02-25 | 2014-02-25
CreateLost |  |  |  | closed
SearchLosts | Design not compatible with mobile | high | bug | open | 2014-02-25
Create New Lost | Error messages not compatible with it's fields | high | bug | closed | 2014-02-24 | 2014-02-24 | 2014-02-24
SearchLost | Design not compatible with mobile | high | bug | open | 2014-02-25
Update Admin | Textboxnedeedfor Status |  |  | open | 2014-02-26